## Overview
AI Testing Automation Plan: Jira to Report
Goal | A Jira test case goes in. The pipeline generates a feature file, step definitions and page objects, runs the tests, analyses failures, suggests fixes, and publishes a report. Humans approve anything that changes code.
Plan start date | 2026-10-05 | Edit this date (yellow cell). All phase dates on the 'Phased Plan' tab recalculate.
Schedule summary
Total weeks (min) | 13
Total weeks (max) | 14
Planned finish (uses max weeks) | 2027-01-10
First milestone, weeks (Phases 0-1, min) | 3
First milestone, weeks (Phases 0-1, max) | 4
Phases done | 0
Progress | 0%
Assumptions
1. Week estimates are rough, for one person working part-time. They are planning estimates, not commitments.
2. Phase 1 is a 1-2 week range; the schedule uses the max so the dates are conservative.
3. Phases run back to back with no overlap or buffer. Edit min/max weeks on the 'Phased Plan' tab to change the schedule.
4. The start date (2026-10-05) is a placeholder assumption; set your own.

## Architecture
Layer | Responsibility | Tools
Input | Pull test cases | mcp-atlassian / Jira REST
Orchestration | Runs the workflow as a graph | LangGraph (or LangChain4j)
AI | Generate tests, analyse failures, suggest fixes | Claude API or Ollama
Automation | Execute tests | Cucumber-JVM, JUnit 5, Playwright / Selenium, Rest Assured, Appium
Quality and safety | Validate, evaluate, scan | Pydantic, Guardrails AI, LLM Guard, promptfoo / DeepEval
Observability and reporting | Trace and report | Langfuse, Allure / ReportPortal
Delivery | Run it reliably | Docker, Jenkins

## Phased Plan
Phased plan (dates calculate from the start date on the Overview tab; blue = editable inputs)
Phase | Name | What to build | Min weeks | Max weeks | Done when | Start | End | Status | Notes
0 | Baseline | A small stable Java suite (UI + API) with Cucumber, Maven, Allure, running in Jenkins | 2 | 2 | Suite runs green in CI with a report | 2026-10-05 | 2026-10-18 | Not started
1 | Jira to feature file | Fetch a ticket, prompt the LLM, validate output with Pydantic, write a .feature file | 1 | 2 | 10 sample tickets produce reviewable features | 2026-10-19 | 2026-11-01 | Not started
2 | Step definitions and page objects | LLM generates glue code and page classes into your repo as a branch or PR | 2 | 2 | Generated code compiles and passes on a simple flow | 2026-11-02 | 2026-11-15 | Not started
3 | Execution and failure capture | Run tests in Docker; collect logs, screenshots, traces, DOM snippets | 1 | 1 | Every failure has a bundle of evidence | 2026-11-16 | 2026-11-22 | Not started
4 | AI root cause and suggested fix | Feed the evidence to the LLM, get a diagnosis and a diff | 2 | 2 | Diff opens as a PR; nothing auto-merges | 2026-11-23 | 2026-12-06 | Not started
5 | Evaluation gate | Regression set of tickets and failures; run promptfoo / DeepEval in Jenkins | 1 | 1 | A prompt or model change that lowers quality fails the build | 2026-12-07 | 2026-12-13 | Not started
6 | Safety and observability | Injection scanning on Jira text, edit restrictions, Langfuse tracing | 1 | 1 | You can replay any agent run and see what the LLM saw | 2026-12-14 | 2026-12-20 | Not started
7 | Multi-agent and RAG | Split into generator, reviewer and analyst agents; retrieve past tests and defects | 2 | 2 | Fewer rejected generations; better root-cause accuracy | 2026-12-21 | 2027-01-03 | Not started
8 | Dashboard | Allure / ReportPortal plus AI metrics | 1 | 1 | Root-cause accuracy, fix acceptance rate and cost per run are visible | 2027-01-04 | 2027-01-10 | Not started
| Total |  | 13 | 14
Formulas:
Start = [End, row above]+1
End = [Start]+[Max weeks]*7-1

## Rules
# | Rule to keep from day one | Followed?
1 | Human approval before merging any generated test or fix. | No
2 | Treat Jira content as untrusted input. | No
3 | Start with Ollama for experiments; use a hosted model where quality matters and policy allows. | No
4 | Measure everything: if you can't score the AI output, you can't improve it. | No
5 | Fix the AI's output format with schemas, not prompt wording alone. | No

## Risks
Risk | Mitigation | Owner | Status
Generated tests pass but test the wrong thing | Human review plus an evaluation set with expected scenarios |  | Open
Flaky tests mistaken for real bugs | Have the root-cause step classify as product bug, test bug, environment or flaky |  | Open
Hallucinated locators or APIs | Give the agent the real DOM or OpenAPI spec as context |  | Open
Cost creep | Cache, trim context, and track cost per run in Langfuse |  | Open
Sensitive data leakage | Mask data before sending, or use local models |  | Open